## Sheet1
Bug # | Found by | Date | Summary/Description | Resolved by | Status? (fixed/open) | Date | Notes
1 | Emma | 2013-05-28 | Notes all fall at the same time. | Emma | Fixed | 2013-05-30 | Made each note come at a random number between 1 and 300. This was done by making arraylists with the four notes and giving them a number between 1 and 4. If one of these numbers were to be created out of a toal of 300 choices, a corresponding note would appear on the screen.
2 | Group | 2013-05-27 | Points could only add and would not subtract for missed notes | Becca | Fixed | 2013-06-03 | Used an else-if statement instead of an if statement. This defined where the note had to be inorder to lose points
3 | Group | 2013-06-04 | Trying to upload song but stuff is blocked. |  | Fixed
| Kyrstle and Lia | 2013-06-07 | Trying to make a timer when the song ends. When we add the timer the notes won't go or the timer just won't work at all. | Becca and Emma